## Test Cases
TC ID | Module | Test Case | Preconditions | Test Steps | Expected Result | Actual Result | Status | Priority
TC001 | Home Page | Check that the home page loads properly. | The website is reachable | Open https://automationexercise.com | The home page should load error-free. | The home page has successfully loaded. | Pass | High
TC002 | Registration | Check the Registration of New Users | User is not registered | Click Signup/Login, enter name and email then click signup | Successful creation of a new account should occur. | The account was successfully created. | Pass | High
TC003 | Login | Make sure your login credentials are valid. | There is a registered user. | Open Login page, enter valid email and password and click Login. | The user should have successfully logged in. | Successful login | Pass | High
TC004 | Login | Check Your Login with Incorrect Credentials | Not a single | Open Login page, enter invalid email and password and click Login. | The proper error message ought to appear. | The error message was successfully displayed. | Pass | High
TC005 | Logout | Check the functionality of the logout | The user is signed in. | Click Logout. | The user should be taken to the login page after being logged out. | Successful logout | Pass | Medium
TC006 | Products | Check the Display of the Products Page | The website is accessible. | Click Products from navigation menu. | The goods page ought to show every product that is available. | The Products page was successfully displayed. | Pass | High
TC007 | Search | Check for Current Products | The Products page is accessible. | Enter Blue Top in search box and click Search. | The corresponding product ought to be shown. | The matching product was successfully displayed. | Pass | High
TC008 | Search | Check for Non-existent Products | The Products page is accessible. | Search for Laptop. | The message "No products found" ought to appear. | There were no products that matched. | Pass | Medium
TC009 | Product Details | Check the Product Details Page | The Products page is accessible. | Click View Product for any product. | Product details ought to be accurately displayed. | Product details were successfully displayed. | Pass | High
TC010 | Cart | Check to Add the Product to Your Cart | The Products page is accessible. | Click Add to Cart for any product and click View Cart. | The chosen item needs to be added to the cart. | The product was successfully added. | Pass | High
TC011 | Cart | Check the View Cart | The item has been placed to the cart. | Add a product and click View Cart. | The cart page need to show every item that has been added. | The cart was successfully displayed. | Pass | High
TC012 | Cart | Make sure to remove the item from your cart. | The item is in the cart. | Open Cart and click X beside the product. | The chosen item needs to be taken out of the cart. | The product was successfully removed. | Pass | High
TC013 | Product Details | Check the Selection of Product Quantity | The product details page is accessible. | Open Product Details, change quantity to 3 and add product to Cart. | The chosen quantity should be added to the product. | Product added in the appropriate amount | Pass | Medium
TC014 | Contact Us | Confirm Submission of the Contact Us Form | The website is reachable | Open Contact Us page, fill all mandatory fields and click Submit. | The contact form should be successfully submitted. | The form was successfully submitted. | Pass | High
TC015 | Contact Us | Check the File Upload in Contact Us | The "Contact Us" page is accessible. | Attach a valid file and submit the form. | The file ought to upload properly. | Uploaded file | Pass | Medium
TC016 | Navigation | Check the Home Page Navigation | The user is on a different page. | Click Home from the navigation menu. | The user ought to be taken to the home page. | The home page was successfully displayed. | Pass | Low
TC017 | Login | Check the functionality of the forgotten password. | The login page is accessible. | Open Login page, look for Forgot Password link and attempt to reset the password. | To retrieve the password, the "Forgot Password" option ought to be accessible. | The login page does not have a "Forgot Password" option. | Fail | High
TC018 | Navigation | Check the Products Page Navigation | The website is accessible. | Click Products from the menu. | The Products page ought should load properly. | The Products page was successfully opened. | Pass | Medium
TC019 | Subscription | Verify Email Subscription | Home page is open | Scroll to the footer and enter a valid email and click Subscribe. | Subscription should be successful | Subscription completed successfully | Pass | Medium
TC020 | Products | Verify View Products by Brand | Products page is open | Select any brand | Products belonging to the selected brand should be displayed | Brand products displayed successfully | Pass | Medium
TC021 | Products | Verify Products by Category | Products page is open | Click Women category and select Dress. | Products belonging to the selected category should be displayed | Category products displayed successfully | Pass | Medium
TC022 | Cart | Verify Add More Products Option from Cart | At least one product is added to the cart | Add a product to the cart, click View Cart and check for an Add More Products or Continue Shopping option on the Cart page. | Cart page should provide an Add More Products/Continue Shopping option. | No dedicated Add More Products/Continue Shopping option is available on the Cart page. | Fail | Medium
TC023 | Cart | Verify Confirmation Before Deleting Product | Product is available in the cart | Open the Cart page and click the X/Delete icon beside a product. | A confirmation dialog should appear before removing the product. | Product is removed immediately without any confirmation dialog. | Fail | Medium
TC024 | Checkout | Verify Proceed to Checkout | Product exists in the cart | Open Cart and click Proceed to Checkout | User should be redirected to the Checkout page. | Checkout page opened successfully. | Pass | High
TC025 | Checkout | Verify Billing Address Display | User is logged in | Proceed to Checkout. | Billing address should be displayed correctly. | Billing address displayed correctly. | Pass | High
TC026 | Products | Verify Search After Selecting Category | Products page is open | Select a category and search for a product within that category. | Matching products should be displayed. | Search results displayed correctly. | Pass | Medium
TC027 | Products | Verify Product Filter Functionality | Products page is open | Open the products page and look for filter options such as price, color, size or rating | User should be able to filter products using different criteria. | Product filtering options are not available. | Fail | Medium
TC028 | Products | Verify Product Price Display | Products page is open | Open any product details page. | Product price should be displayed correctly. | Product price displayed successfully. | Pass | High
TC029 | Products | Verify Product Brand Display | Products page is open | Open any product details page. | Brand name should be displayed correctly. | Brand name displayed successfully. | Pass | Medium
TC030 | Products | Verify Product Category Display | Products page is open | Open any product details page. | Product category should be displayed correctly. | Product category displayed successfully. | Pass | Medium
TC031 | Wishlist | Verify Wishlist Functionality | User is logged in | Login to the application, open the Products page and check for a Wishlist option on product cards or product details page. | User should be able to add products to a Wishlist. | Wishlist feature is not available on the website. | Fail | Medium
TC032 | Cart | Verify Move Product from Cart to Wishlist | Product added to Cart | Add a product to the Cart, open Cart and look for a Move to Wishlist option. | User should be able to move products from Cart to Wishlist. | Cart to Wishlist option is not available. | Fail | Medium
TC033 | Cart | Verify Multiple Products in Cart | Products available | Add two different products and open Cart. | All added products should be displayed in the Cart. | Multiple products displayed successfully. | Pass | High
TC034 | Cart | Verify Apply Coupon Functionality | Product added to Cart | Add any product to the Cart, open Cart and look for an Apply Coupon or Promo Code field. | User should be able to enter a coupon code and apply it successfully. | Coupon/Promo Code option is not available. | Fail | Medium
TC035 | Products | Verify Product Image Display | Products page is open | Open any product details page. | Product image should be displayed correctly. | Product image displayed successfully. | Pass | Medium
TC036 | Products | Verify Product Description Display | Product details page is open | Open any product details page. | Product description should be displayed correctly. | Product description displayed successfully. | Pass | Medium
TC037 | Navigation | Verify Home Navigation from Products Page | Products page is open | Click Home from the navigation menu. | User should be redirected to the Home page successfully. | Home page opened successfully. | Pass | Low
TC038 | Subscription | Verify Duplicate Email Subscription | Email already subscribed | Scroll to footer, enter an already subscribed email and click Subscribe. | Appropriate message should be displayed for duplicate subscription. | Duplicate subscription handled successfully. | Pass | Medium
TC039 | Checkout | Verify Billing Address Display | User logged in with products in Cart | Proceed to Checkout. | Billing address should be displayed correctly. | Billing address displayed successfully. | Pass | High
TC040 | Checkout | Verify Delivery Address Display | User logged in with products in Cart | Proceed to Checkout. | Delivery address should be displayed correctly. | Delivery address displayed successfully. | Pass | High
TC041 | Checkout | Verify Order Summary | Product added to Cart | Add a product to Cart and proceed to Checkout. | Order summary should display correct product details, quantity, and total amount. | Order summary displayed correctly. | Pass | High
TC042 | Checkout | Verify Order Comment Box | User on Checkout page | Proceed to Checkout and enter comments in the comment box. | User should be able to enter order comments successfully. | Comment entered successfully. | Pass | Medium
TC043 | Payment | Verify Payment Page Navigation | User reaches payment step | Click Place Order from Checkout page. | Payment page should open successfully. | Payment page displayed successfully. | Pass | High
TC044 | Payment | Verify Payment with Valid Card Details | Payment page is open | Enter valid card details and click Pay and Confirm Order. | Payment should be processed successfully and order should be placed. | Payment completed successfully. | Pass | High
TC045 | Payment | Verify Validation for Invalid Card Details | Payment page is open | Enter invalid card details and click Pay and Confirm Order. | Appropriate validation or error message should be displayed. | Validation message displayed successfully. | Pass | High
TC046 | Payment | Verify Cash on Delivery (COD) Payment Option | User is on Payment page | Add a product to Cart, proceed to Checkout, click Place Order and observe available payment methods. | Cash on Delivery (COD) should be available as a payment option. | Cash on Delivery (COD) option is not available. | Fail | High
TC047 | Payment | Verify UPI Payment Option | User is on Payment page | Add a product to Cart, proceed to Checkout, click Place Order and check available payment methods. | UPI payment methods (Google Pay, PhonePe, BHIM, etc.) should be available. | UPI payment option is not available. | Fail | High
TC048 | Order | Verify Successful Order Placement | Valid payment completed | Complete payment using valid card details. | Order should be placed successfully and confirmation message should be displayed. | Order placed successfully. | Pass | High
TC049 | Account | Verify Order History | User has placed at least one order | Login to the application, place an order and check the account section for Order History or My Orders. | User should be able to view previously placed orders. | Order History/My Orders option is not available. | Fail | Medium
TC050 | Account | Verify Delete Account Functionality | User is logged in | Click Delete Account and confirm deletion. | User account should be deleted successfully. | Account deleted successfully. | Pass | High
TC051 | Account | Verify Login after Account Deletion | User account has been deleted | Delete the account and try logging in with the same credentials. | Login should fail with an appropriate error message. | Login failed as expected. | Pass | High
TC052 | UI | Verify Responsive Layout | Website is accessible | Open the website on different screen sizes or resize the browser window. | Website layout should adjust correctly without UI issues. | Layout adjusted correctly on different screen sizes. | Pass | Medium
TC053 | Footer | Verify Footer Links | Home page is open | Scroll to the footer and click each footer link. | Footer links should navigate to the correct pages. | All footer links are working correctly. | Pass | Low
TC054 | Session | Verify User Session after Page Refresh | User is logged in | Login and refresh the browser page. | User session should remain active after page refresh. | User session remained active. | Pass | Medium
TC055 | Performance | Verify Home Page Load Time | Stable internet connection | Open the Home page. | Home page should load within an acceptable time. | Home page loaded within acceptable time. | Pass | Medium
TC056 | Security | Verify Website Loads over HTTPS | Website is accessible | Open the website and check the browser address bar. | Website should load securely using HTTPS. | Website loaded over HTTPS successfully. | Pass | High
TC057 | Navigation | Verify Main Navigation Menu | Website is open | Click Home, Products, Cart, Contact Us, Test Cases, API Testing, and Video Tutorials. | All navigation links should open their respective pages successfully. | All navigation links are working correctly. | Pass | Medium
TC058 | UI | Verify Light/Dark Theme Option | User is logged in | Login and check the header, footer, and account section for a theme switch option. | User should be able to switch between Light and Dark themes. | No Light/Dark theme option is available. | Fail | Low
TC059 | Account | Verify Settings/Profile Management | User is logged in | Login and look for a Settings or Profile Management option. | User should be able to manage profile information and account settings. | Settings/Profile Management option is not available. | Fail | Medium
TC060 | General | Verify Website Accessibility | Website is accessible | Open the website and navigate through major pages (Home, Products, Cart, Contact Us). | All major pages should be accessible without errors. | All pages are accessible and working correctly. | Pass | Medium

## RTM
Requirement ID | Requirement Description | Test Case ID | Priority | Status
REQ001 | Verify Home page loads successfully | TC001 | High | Pass
REQ002 | Verify user registration | TC002 | High | Pass
REQ003 | Verify valid login | TC003 | High | Pass
REQ004 | Verify invalid login | TC004 | High | Pass
REQ005 | Verify logout functionality | TC005 | Medium | Pass
REQ006 | Verify Products page | TC006 | High | Pass
REQ007 | Verify product search | TC007 | High | Pass
REQ008 | Verify search with invalid product | TC008 | Medium | Pass
REQ009 | Verify product details | TC009 | High | Pass
REQ010 | Verify add to cart | TC010 | High | Pass
REQ011 | Verify cart page | TC011 | High | Pass
REQ012 | Verify remove product from cart | TC012 | High | Pass
REQ013 | Verify product quantity | TC013 | Medium | Pass
REQ014 | Verify Contact Us form | TC014 | High | Pass
REQ015 | Verify file upload | TC015 | Medium | Pass
REQ016 | Verify Home navigation | TC016 | Low | Pass
REQ017 | Verify Forgot Password functionality | TC017 | High | Fail
REQ018 | Verify Products navigation | TC018 | Medium | Pass
REQ019 | Verify email subscription | TC019 | Medium | Pass
REQ020 | Verify brand products | TC020 | Medium | Pass
REQ021 | Verify category products | TC021 | Medium | Pass
REQ022 | Verify Add More Products option | TC022 | Medium | Fail
REQ023 | Verify confirmation before deleting product | TC023 | Medium | Fail
REQ024 | Verify Proceed to Checkout | TC024 | High | Pass
REQ025 | Verify Billing Address | TC025 | High | Pass
REQ026 | Verify search after category selection | TC026 | Medium | Pass
REQ027 | Verify Product Filter | TC027 | Medium | Fail
REQ028 | Verify product price | TC028 | High | Pass
REQ029 | Verify product brand | TC029 | Medium | Pass
REQ030 | Verify product category | TC030 | Medium | Pass
REQ031 | Verify Wishlist | TC031 | Medium | Fail
REQ032 | Verify Cart to Wishlist | TC032 | Medium | Fail
REQ033 | Verify multiple products in cart | TC033 | High | Pass
REQ034 | Verify Apply Coupon | TC034 | Medium | Fail
REQ035 | Verify product image | TC035 | Medium | Pass
REQ036 | Verify product description | TC036 | Medium | Pass
REQ037 | Verify Home navigation | TC037 | Low | Pass
REQ038 | Verify duplicate email subscription | TC038 | Medium | Pass
REQ039 | Verify Billing Address display | TC039 | High | Pass
REQ040 | Verify Delivery Address display | TC040 | High | Pass
REQ041 | Verify Order Summary | TC041 | High | Pass
REQ042 | Verify Order Comments | TC042 | Medium | Pass
REQ043 | Verify Payment page | TC043 | High | Pass
REQ044 | Verify payment using valid card | TC044 | High | Pass
REQ045 | Verify invalid card validation | TC045 | High | Pass
REQ046 | Verify Cash on Delivery (COD) | TC046 | High | Fail
REQ047 | Verify UPI Payment | TC047 | High | Fail
REQ048 | Verify successful order placement | TC048 | High | Pass
REQ049 | Verify Order History | TC049 | Medium | Fail
REQ050 | Verify Delete Account | TC050 | High | Pass
REQ051 | Verify login after account deletion | TC051 | High | Pass
REQ052 | Verify responsive layout | TC052 | Medium | Pass
REQ053 | Verify footer links | TC053 | Low | Pass
REQ054 | Verify session after refresh | TC054 | Medium | Pass
REQ055 | Verify page load performance | TC055 | Medium | Pass
REQ056 | Verify HTTPS security | TC056 | High | Pass
REQ057 | Verify main navigation menu | TC057 | Medium | Pass
REQ058 | Verify Light/Dark Theme | TC058 | Low | Fail
REQ059 | Verify Settings/Profile Management | TC059 | Medium | Fail
REQ060 | Verify website accessibility | TC060 | Medium | Pass

## Bug Report
Bug ID | Related TC | Module | Bug Title | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status
BUG001 | TC017 | Login | Forgot Password option is unavailable | Open Login page and check for the Forgot Password link. | User should be able to reset their password using the Forgot Password option. | Forgot Password option is not available. | High | High | Open
BUG002 | TC022 | Cart | No Add More Products option in Cart | Add a product to Cart and open the Cart page. | Cart page should provide an Add More Products or Continue Shopping option. | No Add More Products option is available. | Medium | Medium | Open
BUG003 | TC023 | Cart | Product is deleted without confirmation | Add a product to Cart and click the Delete (X) icon. | A confirmation dialog should appear before deleting the product. | Product is removed immediately without confirmation. | Medium | Medium | Open
BUG004 | TC027 | Products | Product Filter functionality is unavailable | Open the Products page and look for filter options. | User should be able to filter products by price, category, or other criteria. | Product filtering option is not available. | Medium | Medium | Open
BUG005 | TC031 | Wishlist | Wishlist feature is unavailable | Open the Products page and check for a Wishlist option. | User should be able to save products to a Wishlist. | Wishlist feature is not available. | Medium | Medium | Open
BUG006 | TC032 | Cart | Cart to Wishlist option is unavailable | Add a product to Cart and open the Cart page. | User should be able to move products from Cart to Wishlist. | Cart to Wishlist option is not available. | Medium | Medium | Open
BUG007 | TC034 | Cart | Apply Coupon option is unavailable | Add a product to Cart and open the Cart page. | User should be able to enter and apply a coupon code. | Coupon field and Apply Coupon option are not available. | Medium | Medium | Open
BUG008 | TC046 | Payment | Cash on Delivery (COD) payment option is unavailable | Proceed to the Payment page after Checkout. | Cash on Delivery should be available as a payment method. | COD payment option is not available. | High | High | Open
BUG009 | TC047 | Payment | UPI payment option is unavailable | Proceed to the Payment page after Checkout. | UPI payment methods should be available. | UPI payment option is not available. | High | High | Open
BUG010 | TC049 | Account | Order History page is unavailable | Login, place an order, and look for Order History. | User should be able to view previously placed orders. | Order History option is not available. | Medium | Medium | Open
BUG011 | TC058 | UI | Light/Dark Theme option is unavailable | Login and check for a theme switch option. | User should be able to switch between Light and Dark themes. | Theme switch option is not available. | Low | Low | Open
BUG012 | TC059 | Account | Settings/Profile Management option is unavailable | Login and look for Settings or Profile Management. | User should be able to manage account settings and profile information. | Settings/Profile Management option is not available. | Medium | Medium | Open